## Slide 1: Utilization Management Solution Proposal

## Slide 2: Project – Utilization and Case Management AI Automation
Objective: Develop and deploy an AI-powered automation platform designed to revolutionize utilization and case management for healthcare payers. This cutting-edge solution will leverage Generative AI, machine learning, and natural language processing (NLP) to streamline case identification, tracking, and management. By automating routine tasks, predicting case outcomes, and optimizing resource allocation, the platform will empower healthcare organizations to improve decision-making, enhance operational efficiency, and significantly reduce medical costs
In Scope:
All UM and CM cases that are handled by EXL Clinical Operations team
Project Milestones (KPI):
MS 1: Finalize the project scope, objectives, and technical feasibility. Get approval from stakeholders to move forward. (Week 4)
MS 2: Complete the first iteration of machine learning models for utilization reviews and case prioritization, ready for testing and validation. Complete the integration of NLP algorithms for extracting patient data from EHRs, NPL ready for testing within the existing systems. (Week 12)
MS 3: Complete the integration of all AI, ML, and NLP components into the existing case management system, followed by pilot testing and user feedback collection. (Week 16)
MS 4: Deploy the fully integrated system and conduct a post-deployment review for any necessary adjustments or improvements. (Week 20)
Project Risks:
Risk 1: Inaccurate AI predictions or algorithms due to data sufficiency and process knowledge
Risk 2: Delays in project timeline due to unforeseen technical challenges or resource shortages
Risk 3:Changes in data privacy regulations that affect the development or deployment of AI systems
Out of Scope:
Non-AI-Driven Process Improvement: Any manual process improvements not directly related to AI implementation (e.g., staffing changes, non-automation-related software upgrades etc.)
Project Stakeholders (RACI matrix):
Risk Mitigation Plan:
Use an iterative approach for model development, conducting frequent testing and validation with real-world data and conduct thorough pre-implementation assessments to identify integration challenges.
Establish a detailed project plan with realistic timelines and buffer time for unforeseen issues and Stay updated on relevant privacy regulations (e.g., GDPR, HIPAA) and incorporate them into system design.
Key Stakeholders: Analytics team (AT), Clinical Ops team (CO), EXL Clinical SMEs (CS), Client Stake holders (SH)
Tasks | AT | CO | CS | SH
Project Planning & Research | R | R | C | I
AI & ML Model Development and testing | A | R | C | I
NLP Development, integration and testing | A | R | C | I
Case Comparison (AI vs Manual) | R | R | C | I
System Integration & Testing | R | A | C | I
Training, Deployment & Change Management | R | R | R | I
Key messages: Changed the Objective based on discussion with Dr. Vikram

## Slide 3: EXL Health
Source:
Prior Authorization Approvals Accelerated with AI & Automation | Infinx Healthcare
Waystar Authorization Platform | Prior Authorization Solutions
AI-Powered Prior Authorization | Healthcare | Availity
Authorization_Whitepaper.pdf
18 Best Prior Authorization Software In Healthcare for 2025 - The Medical Practice
Industry
Offerings
INFINX
WAYSTAR
AVAILITY
Offerings:
Automatically identifies the need of prior authorization and provides real time insights with reports.
Hybrid approach of automation and human intervention for entities looking for flexibility.
AI Agents to follow up with payers.
Limitations:
Requires manual clinical screening.
No support for concurrent or retrospective reviews.
  Offerings:
  Instantly analyzes requests for prior authorization.
  Automates status update tracking and streamlines the workflow.
  Limitations:
  No real time insights into prior authorization trends.
  Requires manual clinical screening.
  No support for concurrent or retrospective reviews.
  Offerings:
  Streamlines authorization submissions
  Caters to the needs of both payers and providers.
  Provides end-to-end platform for prior authorization.
  Limitations:
  Requires manual clinical screening.
  No support for concurrent or retrospective reviews.

## Slide 4
Point of Evaluation | INFINX | WAYSTAR | AVAILITY | CITIUS TECH
Integration with EHR platforms |  |  |  | 
Automation Level | High | High | High | Nil
AI/ML Integration | High | Nil | Mid | Mid
Agentic AI Capabilities | High | Nil | Nil | Nil
Analytics Capabilities | High | High | High | High
Whole UM process automation | Nil | Nil | Nil | Nil
Industry Offerings Cont.
Industry | Reviews
INFINX | Best for AI and Predictive Analytics in Pre Auth
WAYSTAR | Best for maximizing collections and reducing workloads
AVAILITY | Seamless integration with multiple platforms with help of APIs
CITIUS TECH | Not a AI enabled Agent but more like an assistant tool
Need to investigate it more closely

## Slide 5: Current Process
Intake
Case Prep
Prior Authorization
Concurrent Review
Retrospective Review
Claims Payment and Reimbursement
Clinical Quality Audit
Complaints, Grievances & Appeals
Case creation via telephonic, fax or portal
Case verification
Checking of benefits and eligibility
Allocation and tasking per skill and priority
Review of clinical records
Creation of clinical summary
Selection of appropriate criteria or guidelines
Clinical review and determination
Examination of billed codes and medical records
Determination if edit was appropriately applied to the claim suspected of Fraud, Waste and Abuse
Transaction monitoring, reporting, QA huddles
Feedback sessions
Triage & review appeals and complaints for denied/under paid claims
Clinical appeals review and Provider Notification
Potential Scope for Solution
SNF, LTACH, REHAB, ER, MATERNITY, NICU, DIRECT ADMISSION, Scheduled surgery (IP/OP), Office visit
High to Low Complexity (PA): Complex Spine, PWC/LLP, Simple Spine (Laminectomy) Hip and Knee, Cardiology (LAAC, ILR, EP), Bariatric Surgery, Abdominoplasty/Panniculectomy, Breast surgery, Eyelid Surgery
High to Low Complexity (Conc/Retro): Inpatient, Home Health, Rehabilitative Therapy,
DME rental services, Medication Treatment, & Outpatient (Diagnostic and Surgery)
Urine Drug Testing, Genetics, Infectious Agent, Cardiovascular Disease Risk, Laboratory Testing, Facility ER Auditing, Radiology, Digestive, Integumentary, Anesthesia, Physical Medicine, Infusion
Assess the process performance, review key inputs.
Identifying and driving process improvements through data analysis
Experimental & Investigational
Medical Necessity
Cosmetic
Assistant surgeon
Administration Denial
Non- Efficacious
Process Steps
Services
Note:

## Slide 6: Future State
How will this solution transform the current process?
Process map with solutions
Define timelines and impact